
ACTION PLAN

	Recommendation -California Community College System



	Recommendation
	Tasks
	Responsible

Party


	Timeline

	

	Develop & Provide focused Career Ladders Strategic Assistance
	

	· Disseminate models, practices, tools
· Develop technical resources

· Develop team approach (using college practitioners, expert intermediaries local workforce board leaders
· Develop system technical assistance fund
	· Develop practitioner-based technical assistance model that assembles teams of college practitioners, expert intermediaries and local workforce investment board representatives who have all successfully implemented career ladders model programs

· Incorporate resource request in the agency budget change proposal (BCP) process

· Expand system capacity to provide practitioner-based technical assistance for career ladders program development and implementation, demonstration projects and regional initiatives.

· Include: identification of clear roles and responsibilities, assistance in partnership development and maintenance.
· Collaborate with Community Based Organizations to capitalize on the strengths of each organization to meet goals of Career Ladders programs.

· Develop assistance for local colleges to engage in MOU’s and contracts with local WIBs. 

· Incorporate the creation of a technical assistance fund to use as leverage for other resources from WIBs and philanthropic organizations.  


	CCC-BOG

CCCCO

CLP

Consultation Council


	January 2005 – June 2006

	

	Support, Develop & Evaluate Demonstration Projects
	

	· Leverage funding across CC/WIA systems

· Create bridges to and/or focus on high wage/high growth careers

· Incorporate learning communities, cohort approaches
	· Develop and implement career ladders demonstration projects with community college/CBO/WIB partnerships leveraging public and private resources including community college, WIA and philanthropic resources.  

· Focus on high wage/high growth sectors
· Focus on creation of bridges to career pathways and post secondary education, particularly for disconnected youth

· Create and pilot evaluation tools and models for multi-partner workforce collaborations as part of demonstration projects.


	CCCCO

CLP

Private Foundations

LWDA

EDD

CWIB

WIBs


	Aug 04 –

Dec 06

	

	Link/Integrate Career Ladders into Relevant Programs & Funding Streams
	
	
	

	· EWD, VTEA, Tech Prep

· Matriculation, CalWORKs, EOP&S

· Financial Aid
	· Incorporate Career Ladders priorities into system RFAs
· Incorporate Career Ladders priorities into State Vocational Education Plan
· Integrate Career Ladders priorities into categorical programs serving targeted populations
· Evaluate progress and further integrate Career Ladders priorities into Economic And Workforce Development RFPs
· Increase alignment of EWD Initiative Centers with colleges 

	CCCCO

CLP

EDPAC

Outside Evaluator
	Jan 2004 – Jun 2006

	· 
	
	
	

	· 
	
	
	

	

	
	
	
	

	Provide Career Ladders Seed/Base Funding to all Colleges 

· Support partnership development

· Expand career ladders capacity

· Further program/curriculum design, development and integration

· Address integration of support services/instruction
	· Engage system BCP process

· Incorporate career ladders elements and benchmarks for use of funds.

· Provide colleges across the state with base funding to support the development and maintenance of partnerships with WIBs, Community Based Organizations, Business and Industry, Labor Organizations to develop and articulate regional Career Ladders pathways to high wage/high demand sectors

· Seek sufficient funding to enable colleges to appropriately staff the development and implementation of Career Ladders programs

· Promote curricular and student support service innovation and integration

· Expand and support related professional development for faculty and administrators


	CCCCO/CLP

Consultation Council

BOG

Governor’s Office/DOF

Legislature
	Jan 2005 – Aug 2006

	

	Support Career Ladders Related Student Support Services
	
	
	

	· Counseling Career Services

· CalWORKs

· Multi Partner/Cross Agency     Collaborations 
	· Support system BCPs to strengthen support services

· Enhance integration of financial aid services with career ladders offerings

· Work with state agencies to model and highlight cross agency support services


	CCCCO

Consultation Council

HHSA

CBOs


	Jun 2005 – Aug 2006

	

	Address Barriers to Career Ladders Enrollment
	
	
	

	· Promote cohort-based, learning communities 
·   Address enrollment management issues related to career and technical education
· Consider barriers related to student transition from contract, not-for-credit and non credit to “regular” apportionment 
	· Create a system wide taskforce to develop responses and strategies to mitigate barriers to Career Ladders Programs (i.e. cohort enrollment, small class enrollment, transition from contract to regular enrollment, overcap and non-credit enrollment)


	CCCCO

Consultation Council

BOG
	Jun 2005 – Jun 2006

	

	Continue to Streamline System Processes
	
	
	

	· Curriculum and program approval

· Grant application and tracking

· Reporting requirements
	· Implement BOG adopted policy to streamline by removing system requirements for course and program approval and improve regional and local college processes for program approval

· Implement BOG policy to modify reporting requirements where appropriate

· Continue work to simplify system RFA processes and grant reporting requirements
	CCCCO

Academic Senate

CIOs

Consultation Council
	Aug 04 – Dec 05

	
	
	
	

	Mobilize an information campaign to promote the expansion of Career Ladders programs
	
	
	

	· System level exposure and system-wide promotion of Career Ladders

· Local College benefit

	· Reaffirm and update commitment to Ladders of Opportunity Initiative

· Incorporate Career Ladders into BOG Strategic Planning Process

· Identify funds for campaign

· Highlight existing Career Ladders programs

· Market the work and role of Community Colleges as a part of the workforce development system

· Highlight benefits and benefactors of Career Ladders program

· Work with local workforce and economic development agencies to promote the ability of Career Ladders approach to develop the availability of a qualified workforce.  
	CCC-BOG

CCCCO

CLP

Industry Associations, 

Private Foundations, &

CBO Reps


	Jan 05 – Dec 05
Jan 05 – Dec 05

Jun 05 – Jun 06


	Recommendation –California K-16 Educational Institutions



	Recommendation
	Tasks
	Responsible

Party
	Timeline

	

	Engage K-16 partners in career ladders vision and articulation
	

	· Incorporate School to Career and Tech Prep

· Continue K-12/ROP/Adult Ed/CC articulation

· Continue work on CC-CSU-UC course and program articulation w/ focus on pre transfer major preparation in key fields


	· Map pathways in key fields across all educational systems

· Identify and/or share resources for continued articulation, faculty to faculty dialogue and partnerships around specific career pathways

· Work with Governor, CDE, K-12 on BCP for articulation of career and technical programs 


	CCCCO

Academic Senates

(CCC - UC -CSU)

ICC

CDE/CCCCO


	Jan 05 – Jun 06


	Recommendation –California Workforce System



	Recommendation
	Tasks
	Responsible

Party
	Timeline

	

	Align Priorities for WIA Discretionary Funds
	

	· CC/WIB/Business partnerships

· Career Ladders and Bridges to Careers/College

· High wage/High Demand sectors
	· CCC and Ca Workforce System to align priorities for CCC resources and WIA discretionary Funds.  

· Integrate priorities in system processes and proposals


	CWIB

LWDA

EDD

CCC – BOG

CCCCO
	Jan 05 – Jun 06

	
	
	
	

	Address longstanding barriers to collaboration 
· Eligible Training Provider List (ETPL)

· Tracking, evaluation, accountability tools

· Contracting/procurement processes
	· Create joint task force to craft solutions

· Incorporate into Inter Agency Agreement

· Identify and implement needed regulatory or legislative changes
	BOG/CCCCO

LWDA

EDD

CWIB

Legislature
	Jun 05 – Jun 06

	
	
	
	

	Collaborate with Labor and WFD Agency, EDD, CWIB to:
	
	
	

	· Create large-scale Career Ladders partnerships in key industry sectors
· Create fund for regional Career Ladders initiative
· Secure federal funding for California Career Ladders sector initiatives

	· Work with Governor’s Office to include resources for large scale collaboration around state workforce priorities (such as healthcare).  

· Collaborate with CCCCO to support regional initiatives fund

· Create leverage for California to win federal grants such as the Department of Labor-High-wage/High-growth grant and Community-Based Job Training Grants 


	CCCCCO

BOG

LWDA

EDD

CWIB
	Sep 04 – Jun 06

	
	
	
	

	Refocus Local Workforce Priorities
	
	
	

	· Longer term, post secondary education/training

· Career Ladders and Bridges to careers/college

· Partnership development with college
	· Convene local WIBS and colleges on regional basis

· Work with colleges and WIBs to clarify regulations and WIA timelines

· Include in strategic assistance plan


	CCCCO

WIBs

CWA
	Jun 05- Jun 07

	
	
	
	

	Collaborate with the Employment Training Panel to develop and expand Career Ladders programs
	
	
	

	· Promote successful model collaborations

· Jointly address barriers to college participation

· Advertise and extend appropriate waiver processes (minimum salary requirements, removal o cap on literacy skills training time)
	· ETP Career Ladders to collaborate with CCC to minimize barriers to expansion of Career Ladders programs

· Include ETP tools in strategic assistance
	ETP

EDD

CCCCO
	Jan 05 – Dec 06


	Recommendation –Business, Industry, Labor and CBO’s



	Recommendation
	Tasks
	Responsible

Party
	Timeline

	

	Work with Business, Industry and Labor
	

	· Develop and map Career Ladders pathways

· Connect to labor market demand

· Aggregate training needs

· Advocate, lead and help fund partnerships and Career Ladder sector initiatives
	· Promote the development of externship, internship and work-based learning opportunities as a component of career ladders program

· Identify funds and opportunities for development and mapping of career pathways in high wage/high demand sectors of CA economy

· Advocate, lead and help fund partnerships and sector based Career Ladder initiatives


	CCC – BOG

CCCCO

CWIB

ESP

Foundations

CLP

CA Chamber of Commerce

Industry associations

CA Labor Fed

	Jan 05 – Jun 06


	Recommendation – Foundation Community and Legislature



	Recommendation
	Tasks
	Responsible

Party
	Timeline

	

	Engage the Foundation Community to develop and promote Career Ladders
	

	· Seek collaboration on priorities (RFA development, matching funds, etc.)

· Enhance college competitiveness for grant applications

· Develop private/public partnerships that leverage funds, model collaboration and extend demonstration projects
	· Create external advisory group of foundations to inform system RFP process and priorities

· Invite wide participation and discussion of system career ladders projects and priorities
	CCCCO

CLP

Foundations 

Funders groups
	Dec 04 – Dec 05

	
	
	
	

	Pursue Other State and National funding resources for Career Ladders
	
	
	

	· Secure more grants for career ladders projects 
· Enhance college and system competitiveness for federal and national grants 
· Expand system participation in models and initiatives from other states and national organizations
· Work with California Congressional delegation to explore “earmark” requests
	· Build in grant development as part of strategic assistance

· Leverage system resources to create funding matches and public/private partnerships
· Conduct outreach to national demonstration projects initiatives

· Collaborate with foundations on large scale projects and institutionalization issues

· Work with CA state and federal legislators to develop and secure legislative “earmarks” for career ladder initiatives in key CA industry sectors 
	CCCCO/CLP
Foundations

Funders groups

Legislators

Industry Associations

CBO reps

CA Labor Fed 
	Jan 05 – Jun 06

Jan 05 – Jun 06


The Career Ladders Project 





Page 2 of 11

